## APPLIED
# | Fix | Date UTC | File(s) | Evidence | Status | Fleet | Notes
1 | per_sym_sqlite | 10-02 03:39 | per_sym_store.py NEW, v15_pilot, ez_manage, tradier_manage | backups before_per_sym_sqlite_*; pilot imports :4911/:5094/:8621 | VERIFIED | converged 06:25 (s2/s5 got per_sym_store NEW) | sqlite+JSON snapshot of full defaults+overrides
2 | mac_pull html fix | 10-02 03:36 | tools/mac_pull_sheets_charts.sh | backup before_mac_pull_html_fix | APPLIED | Mac 48749a85; fleet 10262676 (vestigial, runs on Mac) | Mac-side puller; fleet copies unused — no action
3 | backfill_per_sym_store NEW | 10-02 03:26 | tools/backfill_per_sym_store.py | no backup (new file) | APPLIED | Mac only; absent fleet (one-shot tool) | No deploy needed
4 | v15_template_universe | 10-02 05:48 | tools/v15_template_universe.py | mtime+md5 f548e08f | APPLIED | fleet match | No backup found (reapply via file copy)
5 | per_sym_quickconfig | 10-02 05:20 | v12_quick_engine.py | backup before_per_sym_quickconfig | APPLIED | in engine 98bd3e9e fleet-wide | Part of engine chain
6 | quickconfig batch | 10-02 06:11 | v15_pilot.py | autosave c1f058f21 | APPLIED | in pilot e94d28a7 fleet-wide | Marker unpinned
7 | divgates ported entry/exit | 10-02 16:00/16:22 | vec_decisions/ported_entry.py, ported_exit.py | backups before_divgates_* (header-verified) | VERIFIED | DEPLOYED by me 06:25 (was Mac-only) | entry=comment-only; exit=+BT exit_fire_masks OR (functional)
8 | bottomtop family wiring | 10-02 16:46 | v12, ez_manage, tradier_manage, configs, bottom_top_signals | backups before_bottomtop_* + LOCKED row | VERIFIED | converged (engine+modules+configs) | 44 template rows x4; parity 5376+10752 zero-mismatch (lock log)
9 | btemit live emission | 10-02 17:48/18:15 | ez_indicators, tradier_indicators | backups before_btemit_* + LOCKED row | VERIFIED | converged (s2 was stale, fixed 06:25) | Additive only; families default OFF
10 | btfamily template rows | 10-02 16:32 | TEMPLATE_* +44 rows x4 | backups before_btfamily_rows_* | APPLIED | in current TEMPLATE_* + NORM | ENTRY_CONFIRMATION_GATES + EXIT_VELOCITY
11 | v15_npz_augment NEW | 10-02 17:54 | tools/v15_npz_augment.py | md5 c49d36b2 | APPLIED | fleet match | No backup found
12 | daily_template_update run | 10-02 18:07 | TEMPLATE_* (worst-first reorder) | backups before_daily_template_update_* | APPLIED | superseded by later template edits | Moved throttler rows 35/36->3/4 (content identical)
13 | gainpusher batch | 10-02 20:01 | cat_side_defaults.py, per_sym_store, gain_pusher, build_4, daily_update, pilot | backups before_gainpusher_v2* + p1musttest | APPLIED | converged 06:25 (closed RESTORE divergence) | s2/s5 were OLD/MISSING since 01:10 — fixed
14 | qualgate | 10-02 21:13 | v15_pilot.py | backup before_qualgate_202610022139 | APPLIED | in pilot e94d28a7 | Marker unpinned
15 | topconfirm batch + rows | 10-02 21:53/21:59 | v15_pilot.py + TEMPLATE_* | backups before_selltop_topconfirm_* | APPLIED | templates in current set | HLR tightening candidates + per-switch yellows
16 | brokersync batch | 10-02 22:25 | v15_pilot batch + ez_manage brokersync_exitfix | backup before_brokersync_exitfix (3.1MB) | PARTIAL | pilot batch fleet-wide; ez_manage MAC-ONLY | Mac bb7e9f82 vs fleet 2e385d67 — needs deploy decision
17 | forcebypass/365prorata | 10-02 22:46 | v15_pilot.py | backups before_forcebypass/365prorata | APPLIED | in pilot e94d28a7 | + test_confirm_365d_gate_default
18 | selltop S63 engine+twins | 10-02 22:47-23:43 | v12, config, config_tradier, ez_positions_quick + TEMPLATE rows + knobs | backups before_selltop_* + LOCKED row + bible S63 | VERIFIED | converged (engine since superseded by wdopen) | Proof round selltop_eng_20261002 documented in S63
19 | typegate | 10-02 23:43/23:49 | v15_pilot, evaluate_v12, bible | backups before_typegate_* | VERIFIED | converged (evaluate 4fe960b4) | TYPE_MISMATCH markers + test_v15_type_gate
20 | qual_retry_timeout | 10-02 23:42 | v15_pilot.py | backup before_qual_retry_timeout | VERIFIED | in pilot e94d28a7 | QUAL_RETRY_TIMEOUT + COMPLIANCE-TIMEOUT markers
21 | skipalarm | 10-03 00:04/00:35 | v15_pilot.py + bible | backups before_skipalarm_* | VERIFIED | in pilot e94d28a7 | [SKIP-ALARM] + SKIP_ALERT markers
22 | coherence | 10-03 00:52 | v15_pilot.py | backup before_coherence_202610030052 | VERIFIED | in pilot e94d28a7 | :663 row/set coherence + publish coherence test
23 | S2/S5 split experiment | 10-03 01:30 | s2 handover set + s5 obligate variant | S2_S5_EXPERIMENT_20261003.md | REVERTED | both back to stock (peer); leftovers cleaned by me | s2 handover ENGINE persisted to 06:1x; s2 tarball remains
24 | noretest S65 herd + naming | 10-03 02:30/02:40 | tools/v15_local_herd.py + v15_final_naming.py + bible S65 | backup before_noretest_guard (herd) | VERIFIED | fleet 4e9c8210 deployed by me | _protected_qualified + floor+1-eps gate; herds take effect at restart
25 | skipalarm_fix + ddmae | 10-03 01:29/02:21 | pilot; lifecycle_pilot, hires_chart, evaluate_v12, bible | backups before_skipalarm_fix/before_ddmae_* | VERIFIED-PARTIAL | lifecycle/hires/evaluate converged | lifecycle +9 (MAE DD) diff-verified; hires fleet match
26 | S64 defaults-pure + voids | 10-03 02:35-03:10 | pilot (:3146 priors=[]), bible S64, promotions, templates | backups before_template_defaults_nopriors/void_phantom_promos | VERIFIED | code live; 6 phantoms voided (diff verified) | BUT fleet launches still V15_INGEST_BEST=1 (see NOT_APPLIED #5)
27 | boolbold templates | 10-03 03:30 | TEMPLATE_* x4 | backups before_boolbold_fix_* | VERIFIED | TEMPLATE_* converged; NORM rebuilt by me | WT_EXHAUST->False, DC_BREAKOUT_SCORE->15, LH_HL native bool
28 | xlsx_truth + revoke | 10-03 02:15/03:49 | v15_pilot.py | backups before_xlsx_truth/before_revoke_* | VERIFIED | in pilot e94d28a7 | :1521 peer-cleanup + :3381 publish-revoked markers
29 | hollowfix + settlefix | 10-03 03:38/04:22 | pilot + v15_row_guards + v15_hollow_scrub | backups before_hollowfix/before_settlefix_* | VERIFIED | guards converged (bca4d0f/f1de64f) | policy stamps + RULE#3 + HOLLOW-REDO; 12/12 tests pass
30 | banrespect_markprice | 10-03 03:56 | ez_positions_service.py +14 | backup before_banrespect_markprice | VERIFIED-FLAG | Mac only (live file, not sweep) | REST poll respects IP ban. FLAG: locked file, no unlock record found
31 | finalbundle + surgery | 10-03 04:06/04:11 | publish_final_winners; per_sym_store.db + per_sym_active_config.json | backups before_finalbundle/before_placeholder_surgery_* | APPLIED | Mac-side publish/data | DB+JSON surgery detail not independently verified
32 | wdopen_kill | 10-03 04:48/04:51 | v12_quick_engine + data/cat_side_defaults_4.json (LIVE x4) | backups before_wdopen_kill_* | VERIFIED-FLAG | engine 98bd3e9e fleet-wide | WATCHDOG_DC_VEC True->False (COTI 4866/5145 fake fires). FLAG: v12 locked, no Oct-3 unlock record; live flip user-ordered, parity-neutral per audit
33 | recalc_onflip | 10-03 ~05:00 | v15_pilot.py | backup before_recalc_onflip_2026100305 | VERIFIED | in pilot e94d28a7 | Live fleet progress shows promoted_how=naked+recalc
34 | addcomptest | 10-03 05:20 | test_v15_row_guards.py | backup before_addcomptest | VERIFIED | tests pass (12/12 incl composition) | verdict/settle composition test
35 | collect-dedupe (mine) | 10-03 06:11 | tools/v15_autopilot.py + tests/test_v15_collect_dedupe.py | backup before_collect_dedupe_202610030611 | VERIFIED | deployed fleet 2397594f; compiles s2/s5 | Newest-per-sym_side before merge; 6/6 tests; fail-open to legacy
36 | fleet converge (mine) | 10-03 06:14-25 | engine/NORM/herd/ported/per_sym/cat_side/gain/build/daily/indicators/CURRENT/fleet_hosts | md5-verified per host; s1 NORM backup autopilot_manual_norm_202610030614 | VERIFIED | ALL match (see FLEET tab) | Closed s2-handover-engine, stale NORMs, RESTORE divergences, CURRENT mismatch
37 | throttler added-switch claim | n/a | TEMPLATE_CRYPTO_SHORT | 93 backups + git blob audit (CHANGES S D) | VOID | n/a | Present since <=Sep-15; 18:07 move was reorder-only. Revert premise void.
38 | quarantine-push | pre-existing | v15_pilot.py :1594-1612 | live: ZENUSDT_SHORT tombstone blocked s1 repeat | FLAWED | in pilot e94d28a7 | Push target hardcodes /home/niels/v15_run25_20261002/progress — breaks run26+. Fix: V15_PROGRESS_DIR.
39 | scheduler quarantine-terminal (mine) | 10-03 06:57 | tools/v15_fleet_scheduler.py + tests/test_v15_quar_terminal.py | backup before_quarterm_202610030657; snapshot quarantined=107 live | VERIFIED | deployed 1c96d52b fleet-wide; attempts reset 233 keys; 9 launches, 0 violations | Probe reports verdict-IMPOSSIBLE; side_state terminal. Root cause of stall: 229 keys at cap.
40 | s2 engine revert 06:28 + restore (mine) | 10-03 06:28/06:5x | s2 v12_quick_engine.py | s2 file mtime 06:28, 771475B = pre-selltop backup image | APPLIED | restored 98bd3e9e, holding; reverter unknown | NEVER-REVERT violation by unknown hand; logged + peers notified
41 | herd stop attempt (mine) | 10-03 06:5x | s1/s2 herd daemons (PIDs 424203/514139 SIGTERM) | ps verified dead, revived <60s (PIDs 3343076/1183120); no cron/timer found | REVERTED-BY-OTHER | herds running latest 4e9c8210, claim+tombstone fenced | Left running (~nil harm); needs user call to kill supervisor/peer intent
42 | best-not-newest publish (mine, unlock v15_pilot.py) | 10-03 07:5x | v15_pilot.py publish block + _rank/_apply_best_publish; tests/test_v15_besteffort.py (22) | backups/before_besteffort_202610030738_*; 22/22 pass; md5 a35d19f4 s1+s2 | VERIFIED | deployed s1+s2; one-time collapse: s1 268 restored/396 demoted, s2 236/110; median active gain 9.89->14.90; quarantine invariant re-guarded (89+67 redemoted) | Qualified beats flagged regardless of gain; ties keep incumbent; losers history-filed, never deleted. s5 fenced, untouched.
43 | NO_TRADES skip (mine, skip-dead-fills order) | 10-03 07:5x | v15_pilot.py below-floor block + SOFT-SKIP/SOFT-REFRESH gates (3 sites) | 22/22 pass incl stamp/hole tests; live on s1+s2 | APPLIED | 0-trade + blockers-empty sheets: XLS kept, sweep skipped, no REDO; rerun only on newer NPZ | Countermands 09-29/30 sweep-anyway. Below-floor-but-trading still sweeps.
44 | BEST_EFFORT near-miss publish (mine, best-effort order) | 10-03 07:5x | v15_pilot.py DONE stage + 365D gate + _nearmiss_30d | 22/22 pass; live on s1+s2 | APPLIED | Valid near-miss (TIM/BH/content, 365D-valid-miss) publishes flagged, no quarantine, no REDO; vomit/invalid still quarantines | 58/90 quarantined are near-miss class (data/reports/quarantine_classes_20261003.json) — retrospective flip proposed, NOT applied.
45 | REDO cap (mine) | 10-03 07:5x | v15_pilot.py 3 REDO sites + _board_has_retryable_holes | 22/22 pass | APPLIED | No REDO when repaired set has 0 trades or content-gate has zero retryable holes; RULE#3/365D-repair REDO kept | Re-fill with identical overrides reproduces identical nulls — pure burn eliminated.
46 | scheduler soft-terminal (mine) | 10-03 07:5x | tools/v15_fleet_scheduler.py HOST_PY probe regex + _VERDICT_TERMINAL_RE; tests/test_v15_quar_terminal.py updated | 6/6 pass incl HOST_PY compile; md5 821e7fda s1+s2; ticks 07:44-48 launching, alert null | VERIFIED | NO_TRADES/BEST_EFFORT join IMPOSSIBLE as terminal (no relaunch, no burn); next round re-evaluates | No herd edit needed (paced loop, fast-exits).
48 | unsettled-none healer | 10-03 09:1x | tools/v15_row_guards.py, tests/test_v15_row_guards.py | row_needs_recalc drops delta-None+empty-reason; dry-run NKE 858/GRAM 734 drops, BABA 0; pytest 19/19 | VERIFIED | 35b228f7 uniform s1/s2/s5 | heals 90k pre-fix identity/crash rows to 0.0-or-values on resume/REDO rebuild; settled verdicts stand
49 | vec_unwired rescue TRADES_PER_SYM_PER_DAY_MAX | 10-03 09:3x | data/vec_unwired.json 162->161 | func-level vec read: overtrade_guard.blocked called from simulate_one L12828; 1622 rows affected | APPLIED | 701fea2d uniform (then extended) | only ledger entry with eval-path read; 156 module-only + 5 no-hit confirmed dead
50 | vec_unwired extend +23 never-movers | 10-03 10:0x | data/vec_unwired.json 161->184 | fleet-strict never (0 nonzero s1+s2+s5) + no func-level vec read + not rescued; 3 live-functional flagged as parity gaps | APPLIED | 16ae46a2 uniform s1/s2/s5 | BOTTOM_EXIT_HTF_WT_VETO/HTF_WT_CHURN/INTRADAY_RATIO_TRIM need engine unlock to test in vec
51 | template greyfix: 127 deletes + 21 sets + FINAL_NORM regen | 10-03 09:2x-09:4x | SPREADSHEETS/TEMPLATE_*.xlsx x4 + TEMPLATE_FINAL_NORM x4 | compat audit 145 fails -> 0; norm unresolved 0/0/0/0; DELTA none->OFF (parity); LR_BAND dict rows untestable removed; 17 bool bolds restored to True | APPLIED | md5 uniform s1/s2/s5 (016d8eb1/f959d797/41fb1cf5/9a55b879) | kills TYPE_MISMATCH/override/INVENTED_ALT/NO_CANDIDATE rows on future boards; backups before_tpl_greyfix_*
52 | v15_switch_healer daemon (s1) | 10-03 22:25 | tools/v15_switch_healer.py NEW, tests/test_v15_switch_healer.py, s1 @reboot cron | dry-runs Mac+s1 clean (peer guard excluded 2+2 movers); 7/7 tests; pid 2087321 live, interval 30m, budget 25/40 | APPLIED | s1-only daemon (code synced fleet-wide d2cb25e7) | audits wiring/live-pos_sym/template each cycle; fixes ledger+templates, journals all, engine gaps to backlog; flock singleton

## NOT_APPLIED
# | Proposal | Source | Target | Blocker / why not | Recommendation
1 | no3m5m/ALL-15m precompute | patches/PENDING_unlock_no3m5m_npzcreator_20261003.md | tools/precompute_v15.py | Needs `unlock tools/precompute_v15.py`; live file still has 3m/5m tfs; before-image stale vs live | Decide single-writer (v8 vs v15) first (NPZ doc containment); user decision supports ALL-15m
2 | master2 value guard (live strip) | patches/PENDING_unlock_master2_valueguard_20261003.md | ez_manage.py, ez_positions_quick.py | SUPERSEDED by user correction: live keeps second/minute/3m/5m | Do NOT apply as written; rewrite for backtest-side only (see #12)
3 | wt15m blocked-side close + parity token | patches/PENDING_unlock_wt15m_blocked_side_close_20261003.md | ez_manage.py + vec_parity_gate.py | Needs `unlock ez_manage.py`; test exists (test_wt15m_blocked_side_close) | Apply after unlock; fixes blocked-side adverse hold; add WT15M_AGAINST token (D4)
4 | brokersync_exitfix deploy | backups before_brokersync_exitfix (Mac bb7e9f82) | fleet ez_manage.py (all 2e385d67) | Never deployed anywhere; needs deploy decision | Decide: deploy to fleet or drop; live-trading file, not sweep
5 | S64 scheduler env (defaults-pure) | bible S64 standing violation | tools/v15_fleet_scheduler.py :326 launch env | Run25 launches V15_INGEST_BEST=1 (chained); mid-round flip would MIX the round | Apply at round boundary: V15_TEMPLATE_DEFAULTS=1 + V15_ADAPT_BASELINE=0
6 | HTF_GATE_D_MANDATORY default-nonzero fix | data/reports/v15_consistency_20261003.md | v12 engine baseline handling | Still flagging (5 syms); needs locked-engine work + proof | Trace evaluate_prepared_sanitized; frozen-baseline gain for running-config value
7 | D1 AUGMENT_MIN_GAIN_PCT 0.0 vs 3.0 | VEC_LIVE_PARITY_AUDIT_20261003.md | live helper + cat_side flip | Vec proofs assumed 0.0, live runs 3.0 | Land live helper + flip live cat_side, or re-verify proofs at 3.0
8 | D3 gated watchdog twin | VEC_LIVE_PARITY_AUDIT_20261003.md | vec + live together | Both sides off (4866 ungated fires were fake) | Land REQ3+ema50+cd+MTF/GR twin on BOTH sides together, then re-verify
9 | D5 sizing parity | VEC_LIVE_PARITY_AUDIT_20261003.md | separate track | Vec floors vs live dynamic sizing | Do not conflate with switch parity; separate workstream
10 | D8 promotion queue | VEC_LIVE_PARITY_AUDIT_20261003.md | S58 repair loop output | Nothing both-positive; queue honestly EMPTY; 365D gate OFF | Repair loop on current engine -> both-positive -> upsert -> cert
11 | D9 promotion probe | VEC_LIVE_PARITY_AUDIT_20261003.md | operator shell step | Needs _psym_get-vs-vec-cfg diff per knob | Run probe before any promotion (type-coercion gaps)
12 | Backtest-side sub-15m parity switch | corrected master2 follow-up | backtest_v12_engine, pilot row-time, tools/opt/* | Needs grep of backtest path for non-vectorized 1m/3m/5m readers | Grep + parity-switch those readers; repoint M7 lint at backtest sources
13 | Full s2/s5 handover revert | CHANGES S E (blocked 01:10) | s2/s5 code+templates | Blocked (locks/NEVER-REVERT); moot | Superseded: fleet converged to LATEST per user order instead
14 | ablation-bolds crypto templates (peer, Mac 06:37) | backups/before_ablation_bolds_20261003_* | SPREADSHEETS/TEMPLATE_CRYPTO_{LONG,SHORT}.xlsx | Bold True->False on ~25 ABLATION rows but is_default NOT flipped -> DEFAULTS-GATE (bold!=YES) would refuse ALL pilots | HELD on Mac; peer must flip L to match + audit clean, then Mac->s1->fleet + NORM rebuild
16 | SHORT WT_DC veto flip | 10-03 09:0x | SPREADSHEETS/TEMPLATE_CRYPTO_SHORT.xlsx (no change) | 14 WT_DC_SHORT_ENABLED=True rows all delta 0.0 with 54-317 trades; ez ignores switch; bold already True in effect | CLOSED-FALSE-ALARM | n/a | no veto active; crypto SHORT boards trade normally
17 | V15_ADAPT_BASELINE flip to 1 | 10-03 09:2x | tools/v15_fleet_scheduler.py:362, tools/v15_local_herd.py:866 (no change) | BABA_SHORT 1656 floor-rows are honest quiet-window outcomes; ADAPT=1 would violate §64 defaults-pure | REJECTED | n/a | ZERO_TRADES/floor rows keep honest 0.0 + reason
18 | DELTA_HTF_GATE none pilot-parse change | 10-03 09:3x | v15_pilot.py:2618 (no change) | vec applies phantom 15m veto for non-TF values (live skips via _B1_REAL_TFS); 'OFF' is parity-correct in both | SUPERSEDED | n/a | fixed in template instead (none->OFF x3); vec/live gap on hh_hl_4h/4h_D stays engine backlog

## FLEET
File | Mac md5 | s1 | s2 | s5 | Status
v12_quick_engine.py | 98bd3e9e | 98bd3e9e | 98bd3e9e | 98bd3e9e | MATCH (engine cut 06:1x; in-flight keep old)
v15_pilot.py | e94d28a7 | e94d28a7 | e94d28a7 | e94d28a7 | MATCH
tools/v15_autopilot.py | 2397594f | 2397594f | 2397594f | 2397594f | MATCH (collect-dedupe; next tick live)
tools/v15_fleet_scheduler.py | 1c96d52b | 1c96d52b | 1c96d52b | 1c96d52b | MATCH (quarantine-terminal; S64 env still INGEST_BEST)
tools/v15_local_herd.py | 4e9c8210 | 4e9c8210 | 4e9c8210 | 4e9c8210 | MATCH (running herds take effect at restart)
tools/v15_final_naming.py | b894a1fc | b894a1fc | b894a1fc | b894a1fc | MATCH (was Mac-only)
tools/v15_row_guards.py | bca4d0f | bca4d0f | bca4d0f | bca4d0f | MATCH
tools/v15_hollow_scrub.py | f1de64f | f1de64f | f1de64f | f1de64f | MATCH
tools/opt/evaluate_v12.py | 4fe960b4 | 4fe960b4 | 4fe960b4 | 4fe960b4 | MATCH
tools/opt/lifecycle_pilot.py | 8a793631 | 8a793631 | 8a793631 | 8a793631 | MATCH
tools/opt/hires_chart.py | 46af79ac | 46af79ac | 46af79ac | 46af79ac | MATCH
vec_decisions/ported_entry.py | b45f93c8 | b45f93c8 | b45f93c8 | b45f93c8 | MATCH (deployed 06:25; was Mac-only)
vec_decisions/ported_exit.py | 69eb9f31 | 69eb9f31 | 69eb9f31 | 69eb9f31 | MATCH (deployed 06:25; was Mac-only)
vec_decisions/bottom_top_signals.py | abb55283 | abb55283 | abb55283 | abb55283 | MATCH
per_sym_store.py | 51d3308d | 51d3308d | 51d3308d | 51d3308d | MATCH (s2/s5 NEW 06:25; was MISSING)
cat_side_defaults.py | 51304a64 | 51304a64 | 51304a64 | 51304a64 | MATCH (s2/s5 updated 06:25; was OLD c820066d)
ez_indicators.py | bbd31d0e | bbd31d0e | bbd31d0e | bbd31d0e | MATCH (s2 was stale, fixed 06:25)
tradier_indicators.py | f786be92 | f786be92 | f786be92 | f786be92 | MATCH (s2 was stale, fixed 06:25)
tools/v15_gain_pusher.py | 0bce3bdf | 0bce3bdf | 0bce3bdf | 0bce3bdf | MATCH (s2/s5 updated 06:25)
tools/build_cat_side_defaults_4.py | e4fc64c4 | e4fc64c4 | e4fc64c4 | e4fc64c4 | MATCH (s2/s5 updated 06:25)
tools/v15_daily_template_update.py | 8d58d0db | 8d58d0db | 8d58d0db | 8d58d0db | MATCH (s2/s5 updated 06:25)
tools/v15_template_universe.py | f548e08f | f548e08f | f548e08f | f548e08f | MATCH
tools/v15_npz_augment.py | c49d36b2 | c49d36b2 | c49d36b2 | c49d36b2 | MATCH
tools/v15_template_normalize_defaults.py | 5aa21693 | 5aa21693 | ? | ? | s1 verified (ran rebuild); s2/s5 not checked (s1-only stage)
TEMPLATE_CRYPTO_LONG.xlsx | src c186d19b | src match | src match | src match | MATCH (sources)
TEMPLATE_CRYPTO_SHORT.xlsx | src 1f456878 | src match | src match | src match | MATCH (sources)
TEMPLATE_STOCKS_LONG.xlsx | src c7553a96 | src match | src match | src match | MATCH (sources)
TEMPLATE_STOCKS_SHORT.xlsx | src 2a928138 | src match | src match | src match | MATCH (sources)
NORM TEMPLATE_CRYPTO_LONG | (stale Mac) | 9bd14914 | 9bd14914 | 9bd14914 | MATCH (rebuilt s1 06:14 from current sources; Mac NORM stale by design — s1 is truth)
NORM TEMPLATE_CRYPTO_SHORT | (stale Mac) | 53d921e8 | 53d921e8 | 53d921e8 | MATCH (rebuild fixed 2 CRYPTO_SHORT groups)
NORM TEMPLATE_STOCKS_LONG | (stale Mac) | d47101b9 | d47101b9 | d47101b9 | MATCH
NORM TEMPLATE_STOCKS_SHORT | (stale Mac) | e0c30d16 | e0c30d16 | e0c30d16 | MATCH
data/engine_deploy/CURRENT.json | 98bd3e9e | 98bd3e9e | (absent) | (absent) | Mac+s1 truthful 06:16 (was 0b43055f vs 75329b59 = Monday ABORT); s2/s5 never had it
tools/fleet_hosts_final.json | s1+s2 (live) | s1+s2 (live) | n/a | n/a | s5 fenced 06:15 by peer verify job; Mac synced from s1; restore: ~/v15_s5verify_fence*.json
ez_manage.py | bb7e9f82 | 2e385d67 | 2e385d67 | 2e385d67 | INTENDED DRIFT (brokersync fix Mac-only; needs deploy decision)
tools/mac_pull_sheets_charts.sh | 48749a85 | 10262676 | 10262676 | 10262676 | INTENDED (runs on Mac; fleet copies vestigial)
tools/backfill_per_sym_store.py | ef83b85a | (absent) | (absent) | (absent) | INTENDED (Mac one-shot tool)
tools/precompute_v15.py | 1db7637c (3m/5m) | ? | ? | ? | NOT DEPLOYED (no3m5m pending; do not run either precompute mid-campaign)
~/binance/ mirrors | n/a | stale | stale b80f8f5c | ? | STALE (scheduler root is sandbox; mirrors untouched since experiment)

## ROUND_STATUS
Key | Value
Round | run25 (started 2026-10-02 21:50Z on PREVIOUS defaults after run24 collect GAVE UP on dupe assert)
Phase / alert | sweep / None (healthy); ticks every 2 min; autopilot every 5 min
Coverage 06:20Z | CL 18% (9/50), CS 26% (13/50), SL 8.2% (8/97), SS 11.6% (10/86); done=40, pending symbols 143
Launch env | V15_FRESH_RUN=1 V15_INGEST_BEST=1 V15_ADAPT_BASELINE=1 (S64 violation — chained, not defaults-pure)
s5 fence | Removed from scheduler 06:15 by peer ivory-metis for user-ordered s5_verify_20261003 (scalar live-verify, 490 finals). s1/s2 sweep on. Restore when peer reports done.
No-repeat proof | Scheduler owner/held+attempts; herd claims+[claim-skip]+S65; pilot DEDUP lock+tombstone (ZENUSDT_SHORT: s2 quarantined, s1 MUST-NOT-RETOUCH); collect-dedupe guards round-end
Dupe forensics | run25 cross-host same-name progress files (s1n s2=36, s1n s5=40, s2n s5=19) are SYNC COPIES (identical bytes/mtime) or tombstones — NOT double-computes (proven via /tmp sweep logs per host)
Mixed-round caveat | run25 spans 3 engines + 3 NORM builds across time; in-flight pilots drain on old code. Never average across defaults rounds (S60.6); interpret run25 aggregates accordingly
Watch items | 1) Pair-constraint trickle (empty ticks with free slots) — adopted/chain paths should drain singles. 2) Quarantine-push hardcodes run25 path — fix before run26. 3) Sync fan-out mechanism unidentified (harmless copies). 4) Monday 06:00 final phase interrupts run25 regardless.
Quarantine (07:00Z) | 107 sym_sides verdict-IMPOSSIBLE, now terminal (no relaunch, no burn)
Attempts reset (07:00Z) | 233 keys cleared (backup fleet_scheduler_state.before_quarterm_20261003.json); 07:02 tick launched 9, 0 violations
Herds | Running latest on s1/s2 despite stop attempt (revived <60s, supervisor unknown); fenced, ~nil harm; user call pending
Mac template drift | Crypto TEMPLATE_* 06:37 ablation-bolds HELD (gate-breaking); fleet on gate-clean boolbold set
Best-publish (07:50Z) | LIVE s1+s2 (pilot a35d19f4, sched 821e7fda); book median gain 9.89->14.90; 446 single-best actives (4 unparseable left, reported)
Dead-fill skip (07:50Z) | LIVE: 0-trade sheets skip sweep+REDO, rerun on NPZ refresh only
Near-miss policy (07:50Z) | LIVE prospectively; 58 quarantined are near-miss class — retrospective BEST_EFFORT flip awaiting user call
Pre-existing test failures | test_v15_pilot x2 (missing TEMPLATE.xlsx + absent string, proven in backup) + test_hao_finished_broken (Mac-local None deltas) — untouched, not mine